## Sheet1
Date | Notes
2019-05-20 | First day
2019-05-21 | Onboarding, setting up accounts, etc
2019-05-22 | Computer locked out, worked from uni on collecting lit
2019-05-23 | Onboarding, setting up accounts, etc
2019-05-24 | Setting up writing document
2019-05-27 | Started working on core functionality, program takes in a list of authors and tweets, uses the author and @s to build and edge list, feeds the edgelist into the networkx package, generates netwrok statsitics for each user in the network and then reports the top 10
2019-05-28 | Work on core program
2019-05-29 | Work on core program, added basic graphing
2019-05-30 | Work on core program, wrapped in twitter bot for demonstration
2019-05-31 | Feedback on core program that they are intrested in an input user rather than top 10, and also that they can't show nonvalidated users in the results, not intrested in the twitter bot functionality
2019-06-03 | Implimented hashing function to hide all accounts other than the valid user
2019-06-04 | Reworked main program to authenticate from Twitter to get more data
2019-06-05 | Investigated methods for identifying valid users
2019-06-06 | Implmented basic method for getting valid users from tweet objects, can get senders, but not recivers
2019-06-07 | Worked on setting up write up doctument
2019-06-10 | Implimented getting recivers valid status by making extra API calls
2019-06-11 | Recivers can be identified as valid if the tweet is a retweet - added that functionality and now only have to make 20% of API calls otherwise would
2019-06-12 | Adapted hasing so valid users and the given user is shown, built verified user generator which will create a JSON of all verified users so no API calls need to be made by the other scripts
2019-06-13 | Pivoted main program so it displayed the given user in a distribution of valid users based on percentile rank within the network metrics
2019-06-14 | Work on literature
2019-06-17 | Research on better graphing tools
2019-06-18 | Added a better graphing tool which is written in R, python saves data and then calls an R script which takes the data and saves an HTML graph, finally python opens the HTML to show the graph
2019-06-19 | AL
2019-06-20 | Work on verified user generator - will take almost 4 days to run, but should only need run once
2019-06-21 | Revewing literature
2019-06-24 | Built topic modeller script - this takes a given user, scans their sent tweets and returns their most used hashtags and topcis, based on topic modelling
2019-06-25 | Added sentiment analyis to main - it can now report the sentiment of the whole network as well as tweets about the given user
2019-06-26 | Changed mian to use full text by using the extended option in tweepy - but retweet text is in a different place from normal mentions so added if statmenets
2019-06-27 | AL
2019-06-28 | Revewing literature
2019-07-01 | Writing, Looking at previous dissertations and planning the structure of mine, added cheating so tweets send by or about the given user can be added to the network artificially (increases bias)
2019-07-02 | Bugfixing, using full retweeted text (which is the only way to avoid truncated text) cuts off the '@' which stops retweets being used in the network. Have now manually concatinating the frist mention (in a retweet first mention is always the trageted user) back onto each text object
2019-07-03 | Made valid user generator robust to dissconnection and changed it to output a dictonary of ID:screen_name so that in future fast searches can be performed on the ID which is faster to get. Added time feature to topic modeller so you can ask for tweets from X days ago only. Started building sentiment checker.py which will scan for mentions of a user (with the option of adding a topic) and will return the sentiment score of those tweets
2019-07-04 | Fixing disconnection bug in Verified_users_generator, building sentiment checker.py
2019-07-05 | Looking at example dissertations
2019-07-08 | Checking verified user script works, adding rolling comparison to main - it now compares some stats with the previous run using txt files as storage, identifying buiness value (Probably in tracker as as a way to track the impact of social media campaigns, identify users who are helping spread or should be contacted to help spread, identify the sentiment of the campaign)
2019-07-09 | Modifying verified users script as it failed on a non-existant user over night. Set it running again. Reading example dissertations
2019-07-10 | Started writing intro of dissertation, annotating code, making implementation mockup
2019-07-11 | Writing intro of dissertation, working on mock up
2019-07-12 | Bug fixing main code
2019-07-15 | Reviewing literature at university
2019-07-16 | Working on fixing verifies users generator
2019-07-17 | Making poster for poster session, writing some of State of the art section
2019-07-18 | Writing some of methods section, making powerpoint for presentation next week
2019-07-19 | Working on presentation for feedback session, testing of verified users generator code
2019-07-22 | Medical leave
2019-07-23 | Feedback workshop at Barrachd
2019-07-24 | Medical leave
2019-07-25 | AL
2019-07-26 | Medical leave
2019-07-29 | Spell checking and improving code comments
2019-07-30 | Technical workshop at Barrachd demonstrating code, added sentiment analysis to topic modeller
2019-07-31 | Poster session, uni of Stirling
2019-08-01 | AL
2019-08-02 | Supervision with Gabrila and then worked from the uni
2019-08-05 | AL
2019-08-06 | Writing dissertation - first half of Network analyiser section done
2019-08-07 | Writing dissertation - second half of Network analyiser and most of topic modeller done
2019-08-08 | Trains off, worked from uni on writing disseration - primarily doing captioning
2019-08-09 | Barrachd placement ends.
2019-08-10
2019-08-11
2019-08-12
2019-08-13
2019-08-14
2019-08-15
2019-08-16
2019-08-17
2019-08-18
2019-08-19
2019-08-20
2019-08-21
2019-08-22
2019-08-23
2019-08-24
2019-08-25
2019-08-26
2019-08-27
2019-08-28
2019-08-29
2019-08-30
2019-08-31
2019-09-01
2019-09-02
2019-09-03
2019-09-04
2019-09-05
2019-09-06